## Slide 1: Management of Software Engineering

## Slide 2: Outline
Why is management needed?
What are the main tasks of managers?
What is special in the case of software?
How can productivity be measured?
Which tools may be used for planning and monitoring?
How can teams be organized?
How can organizations' capabilities be defined and measured?

## Slide 3: Management
Software engineering projects involve many software engineers
Management is needed to coordinate the activities and resources involved in projects
"The creation and maintenance of an internal environment
in an enterprise where individuals, working together in
groups, can perform efficiently and effectively toward the
attainment of group goals" (Koontz et al, 1980)

## Slide 4: Management tasks
Planning
Organizing
Staffing
Directing
Controlling
… and dealing with deviations from the plan
“Plan the work and work the plan”

## Slide 5: Management challenges
Balance conflicting goals
Deliver a high-quality product with limited resources
Organize an activity that is fundamentally intellectual
  this complicates the traditional techniques for productivity measurement, project planning, cost and schedule estimation

## Slide 6: Software productivity
How to define/measure it?
In terms of lines of code produced
  few tens per day
.. but what do engineers do?
  up to half their time spent in meetings, administrative matters, communication with team members

## Slide 7: Function points
A productivity measure, empirically justified
Motivation: define and measure the amount of value (or functionality) produced per unit time
Principle: determine complexity of an application as its function point

## Slide 8: Function point definition
A weighted sum of 5 characteristic factors

## Slide 9: A byproduct
Function points used to measure the relative power of different languages
  compute number of source lines required to code a function point
  numbers range from 320 (assembler languages), 128 (C), 91 (Pascal), 71 (Ada83), 53 (C++, Java), 6 (“spreadsheet languages”)

## Slide 10: Size of code
Size of code produced per unit of time as productivity measure
  must define exactly what "size of code" means
    delivered source instructions (DSI)
    noncommented source statements (NCSS)
.. but how good is this metric?

## Slide 11: Factors affecting productivity
Professionals' capabilities
Product complexity
Schedule constraints
Previous experience
(Overly aggressive scheduling may have negative effect)

## Slide 12: People and productivity
Because software engineering is predominantly an intellectual activity, the most important ingredient for producing high-quality software efficiently is people
Large variability in productivity between engineers

## Slide 13: Cost estimation
We need predictive methods to estimate the complexity of software before it has been developed
  predict size of the software
  use it as input for deriving the required effort

## Slide 14: Generic formula for effort
PM = c.KLOCk
Legend
  PM: person month
  KLOC: K lines of code
  c, k depend on the model
  k>1 (non-linear growth)
Initial estimate then calibrated using a number
of "cost drivers"

## Slide 15: Typical cost driver categories
Product
  e.g., reliability requirements or inherent complexity
Computer
  e.g., are there execution time or storage constraints?
Personnel
  e.g., are the personnel experienced in the application area or the programming language being used?
Project
  e.g., are sophisticated software tools being used?

## Slide 16: Cost estimation procedure
Estimate software size, and use it in the model’s formula to get initial effort estimate
Revise estimate by using the cost driver or other scaling factors given by the model
Apply the model’s tools to the estimate derived in step 2 to determine the total effort, activity distribution, etc.

## Slide 17: COCOMO models Constructive Cost Model
  proposed by B. Boehm
  evolved from COCOMO to COCOMO II

## Slide 18: COCOMO
Size estimate based on delivered source instructions, KDSI
Categorizes the software as:
  organic
  semidetached
  embedded
    each has an associated formula for nominal development effort based on estimated code size

## Slide 19
Mode
Feature
Organic
Semidetached
Embedded
Organizational understanding of
product objectives
Thorough
Considerable
General
Experience in working with related
software systems
Extensive
Considerable
Moderate
Need for software conformance with
pre
-
es
tablished requirements
Basic
Considerable
Full
Need for software conformance with
external interface specifications
Basic
Considerable
Full
Concurrent development of
associated new hardware and
operational procedures
Some
Moderate
Extensive
Need for inn
ovative data processing
architectures, algorithms
Minimal
Some
Considerable
Premium on early completion
Product size range
Low
<50 KDSI
Medium
<300 KDSI
High
All sizes

## Slide 20: COCOMO nominal effort and schedule equations

## Slide 21
Ratings
Cost Drivers
Very low
Low
Nominal
High
Very
High
Extra
High
Product attributes
Required software
reliability
.75
.88
1.00
1.15
1.40
Data base size
.94
1.00
1.08
1.16
Product complexity
.70
.85
1.00
1.15
1.30
1.65
Comput
er attributes
Execution time constraints
1.00
1.11
1.30
1.66
Main storage constraints
1.00
1.06
1.21
1.56
Virtual machine volatility*
.87
1.00
1.15
1.30
Computer turnaround time
.87
1.00
1.07
1.15
Personnel attributes
Anal
yst capability
1.46
1.19
1.00
.86
.71
Applications experience
1.29
1.13
1.00
.91
.82
Programmer capability
1.42
1.17
1.00
.86
.70
Virtual machine
experience*
1.21
1.10
1.00
.90
Programming language
experience
1.14
1.07
1.00
.95
Project
attributes
Use of modern
programming practices
1.24
1.10
1.00
.91
.82
Use of software tools
1.24
1.10
1.00
.91
.83
Required development
schedule
1.23
1.08
1.00
1.04
1.10
COCOMO
scaling
factors

## Slide 22: Towards COCOMO II
COCOMO's deficiencies
  strictly geared toward traditional development life cycle models
    custom software built from precisely stated specifications
  relies on lines of code

## Slide 23: COCOMO II
A collection of 3 models
  Application Composition Model
  Early Design Model
  Post-Architecture Model

## Slide 24: Application Composition Model
Suitable for software built around graphical user interface (GUI) and modern GUI-builder tools
Uses object points as a size metric
  extension of function points
  count of the screens, reports, and modules, weighted by a three-level factor (simple, medium, difficult)

## Slide 25: Early Design Model
Used once requirements are known and alternative software architectures have been explored
Cost prediction based on function points and coarse-grained cost drivers
  e.g., personnel capability and experience

## Slide 26: Post-Architecture Model
Involves actual software construction and software maintenance
Cost prediction based on
  size (either as source instructions or function points, with modifiers to account for reuse)
  7 multiplicative cost drivers
  5 factors that determine the non linear growth of person-month costs in terms of size

## Slide 27: Project control

## Slide 28: Work Breakdown Structure
WBS describes a break down of project goal into intermediate goals
Each in turn broken down in a hierarchical structure

## Slide 29
Example: a compiler project

## Slide 30: Gantt charts
A project control technique
Defined by Henry L. Gantt
Used for several purposes, including scheduling, budgeting, and resource planning

## Slide 31
Example: a compiler project

## Slide 32
1/1
4/1
7/1
10/1
Darius
Marta
Leo
Ryan
Silvia
Laura
vacation
vacation
vacation
vacation
vacation
training
training
training
training
training
training
Example: scheduling activities

## Slide 33: PERT Charts
PERT (Program Evaluation and Review Technique) chart
  network of boxes (or circles)
    representing activities
  arrows
    dependencies among activities
      activity at the head of an arrow cannot start until the activity at the tail of the arrow is finished

## Slide 34
Example: a compiler project

## Slide 35: Analysis of PERT charts
Critical path for the project (shown in bold)
  any delay in any activity in the path causes a delay in the entire project
    activities on the critical path must be monitored more closely than other activities

## Slide 36: Gantt & PERT charts
Force the manager to plan
Show interrelationships among tasks
  PERT clearly identifies the critical path
  PERT exposes parallelism in the activities
    helps in allocating resources
Allow scheduling and simulation of alternative schedules
Enable the manager to monitor and control project progress and detect deviations

## Slide 37: Organization
An organization structure is used to structure the communication patterns among members of a team
Traditional team organization is hierarchical with a manager supervising a group or groups of groups
Other organizations have been tried in software engineering with some success

## Slide 38: Chief-programmer teams
A way to centralize the control of a software development team
  chief programmer (CF) responsible for design + reports to peer manager responsible for administration
  other members are a software librarian and programmers
    report to CF and are added to team when needed
Best when the solution may be understood and controlled by one chief architect

## Slide 39
Team structure

## Slide 40: Decentralized team organization
Decisions are made by consensus, and all work is considered group work
Members review each other’s work and are responsible as a group for what every member produces
Best when the problem or solution is not well-understood and requires the contribution of several people to clarify it

## Slide 41
Team structure
management structure
communication pattern

## Slide 42: Mixed-control team organization
Attempts to combine the benefits of centralized and decentralized control
Differentiates engineers into senior and junior
Senior engineer leads a group of juniors and reports to a project manager
Control vested in the project manager and senior programmers
Communication decentralized among each set of individuals, peers, and their immediate supervisors

## Slide 43
management structure
communication pattern
Team structure

## Slide 44: Case study: open source development
Reliance on volunteer developers and the lack of organized schedule
Team organization is a mixed mode
  each module has a responsible person , who is the ultimate arbiter of what goes into the eventual release of the module
  anyone may review the module and send in corrections and other contributions to the responsible person

## Slide 45: An assessment
Team organization depends on the goals
No team organization is appropriate for all tasks
Decentralized control best when communication is necessary to achieve a good solution
Centralized control best when development speed is key and problem is well understood
An appropriate organization limits the amount of communication to what is necessary to achieve the goals—no more and no less

## Slide 46: Case study: Nokia software factories

## Slide 47: Foundational principles
  Geographically distributed environment
    typical project: 100 developers working in three to four sites
    synchronous work not possible (differences in time zones)
  Product family architecture
    architecture developed for an entire family, and components developed to be used in all family members
  Concurrent engineering
    components developed concurrently at different sites, retrieved from the various sites and combined in a central location
  Use of tools
    process is tool supported (for requirements engineering, design, coding, version management, configuration management, and testing)

## Slide 48: Risk management
A topic of management theory
Identifies project risks, assesses their impact, and monitors and controls them

## Slide 49
RISK
RISK MANAGEMENT TECHNIQUE
1. Personnel shortfalls
-
Staffing with top talent; job matching; team
building; key
-
personnel agreements; cross
-
training; pre
-
scheduling key people
2. Unrealistic schedules
and budgets
-
Detailed multisource cost & schedu
le
estimation; design to cost; incremental
development; software reuse; requirements
scrubbing
3. Developing the wrong
software functions
-
Organization analysis; mission analysis; ops
-
concept formulation; user surveys; prototyping;
early users’ manuals
4. Developing the wrong
user interface
-
Prototyping; scenarios; task analysis; user
characterization (functionality, style, workload)
Typical SE risks (Boehm 1989)

## Slide 50
8. Shortfalls in
externally
performed tasks
-
Reference checking; pre
-
award audits; award
-
fee
contracts; competitive design or prototyping;
team building
9. Real
-
time performance
shortfalls
-
Simulation; benchmarking; modeling;
prototyping; instrumentation; tuning
10. S
training computer
science capabilities
-
Technical analysis; cost
–
benefit analysis;
prototyping; reference checking
5. Gold plating
-
Requirements scrubbing; prototyping; cost
–
benefit analysis; design to cost
6. Continuing stream of
re
quirements
-
High change threshold; information hiding;
incremental development (defer changes to later
increments)
7. Shortfalls in externally
furnished components
-
Benchmarking; inspections; reference checking;
compatibility analysis

## Slide 51: Capability Maturity Model
CMM developed by the Software Engineering Institute to help
  organizations which develop software
    to improve their software processes
  organizations which acquire software
    to assess the quality of their contractors

## Slide 52: Maturity
Immature organization
  processes are improvised during the course of a project to resolve unanticipated crises
  products often delivered late and their quality is questionable
Mature organization
  organization-wide standard approach to software processes, known and accepted by all engineers
  focus on continuous improvement both in performance and product quality

## Slide 53
CMM maturity levels

## Slide 54: Key process areas